## Slide 1: Transportation Improvement Program
Fiscal Year (FY) 2024-2028
Final Draft for July Adoption
TPA Committees

## Slide 2: What is the Transportation Improvement Program?
24
25
26
27
28
List of projects by phase and funding for the next 5 years
Notes: Spending authority in the first year

## Slide 3: TIP Development Process
Project
Development
List of
Priority Projects
(LOPP)
Draft Tentative
Work Program
(DTWP)
Transportation Improvement Program (TIP)
TPA Call for Project Applications:
Project Applications
Feasibility Review
New Project Rankings
Winter - Spring 2022
TPA Adopts: List of Priority Projects for New Outer Year & Provides to FDOT
State Road Modifications
Local Initiatives
Transportation Alternatives
July 2022
FDOT presents draft work program per 339.135, F.S.
December 2022
TPA builds New 5 Year TIP
Presents Draft TIP for FY 24-28 in March 2023
TPA Adopts: Final TIP for FY 24-28 in June 2023
TPA Endorses: requests changes, additions, or deletions
June 2023

## Slide 4: Funding Summary
Chart: 
| Seaport | Airports | O&M - Transit | O&M - Roadways | Major Maintenance | Other FDOT & Local Projects | Transportation Alternatives Program | Local Initiatives Program | State Road Modifications | SIS Capacity
Federal | 4860000 | 133121840 | 75330396 | 84108417 | 10296482 | 74430313 | 100817923 | 171463953
State | 12015083 | 45105154 | 83155988 | 182466969 | 121531701 | 56713728 | 6690027 | 41821900 | 275250361
Turnpike | 332004674 | 66641616 | 1251809760
Local | 5515083 | 26569654 | 460158805 | 210933299 | 76929057 | 177336521 | 5733036 | 17429838 | 2835137 | 1648907
$3.1 Billion Federal/State funding
in Palm Beach County

## Slide 5: LRTP Priorities Summary
Project Category | LRTP 2045 Cost Feasible Plan | Fiscal Year 24-28 TIP |  |  | TPA Priorities Not Committed yet in TIP
 |  | Underway/ Complete | In TIP with CST Phase | In TIP w/o CST Phase | 
Strategic Intermodal System (SIS) (project line items in LRTP) | 45 | 11 | 14 | 7 | 13
TPA Major Priority Projects (project line items in LRTP with CST) | 17 | 4 | 7 | 4 | 3
State Road Modifications (annual submittals) | 15 prioritized | 1 | 3 | 10 | 1
Local Initiatives (annual submittals | 19 prioritized | 0 | 13 | 0 | 6
Transportation Alternatives (annual submittals) | 15 prioritized | 4 | 11 | 0 | 0

## Slide 6: Summary of TPA Priorities
$235 M
Programmed in TIP

## Slide 7: State Road Modifications (SRM)
Yr/Rank | Project
04-1 | SR 7: 60th St to Northlake Blvd – Delayed to >FY 28
04-2 | SR-7: Okeechobee Blvd to 60th St – Delayed to FY 28
14-3 | Atlantic Ave: SR-7 to Lyons Rd – on schedule for FY 24
16-1 | Atlantic Ave: Lyons Rd to Turnpike – on schedule for FY 27 Atlantic Ave: Turnpike to Jog Rd – construction still outside work program
18-1c | Okeechobee Blvd: SR-7 to US-1 – FDOT feasibility study in FY 25
18-3 | US-27 Connector: US-27 to SR-715 – preliminary Project Development study in FY 27
Highlights

## Slide 8: Local Initiatives (LI)
Upcoming Projects in FY 2024
Yr/Rank | Project/Applicant
17-1/5 | 36th St and bridge – West Palm Beach
18-6 | Germantown Rd – Delray Beach
19-1 | Electric Buses and Chargers – Palm Tran
Prioritized, not programmed yet
Yr/Rank | Project/Applicant
22-1 | SW 18th Street Shared Use Path – Boca Raton
22-3 | Gardens Parkway bike lane and sidewalk – Palm Beach Gardens
22-4 | 4 Electric Buses – Palm Tran
22-5 | Barwick Rd Shared Use Path – Delray Beach
22-6 | Bus Stop Improvements – Palm Tran
22-7 | Speed Tables - ITID

## Slide 9: Transportation Alternatives (TA)
Upcoming Projects in FY 2024
Yr/Rank | Project/Applicant
16-2 | North Shore Pedestrian Bridge– West Palm Beach
19-2 | SE 1st shared use path – Boynton Beach
20-3 | Cherry Rd path and lighting – Palm Beach County
20-4 | Bus Stops ADA connections and enhancements – Palm Tran
New projects funded for CST FY 26:
Yr/Rank | Project/Applicant
22-1 | Various Locations – Indian Trail Improvement District (ITID)
22-2 | Fairchild Ave – Palm Beach Gardens
22-3 | 49th St – West Palm Beach
22-4 | Various Locations – Royal Palm Beach

## Slide 10: Programming and Production
24
25
26
27
28
23
Current Fiscal Year
Draft Transportation
Improvement Program (TIP)
“New 5th Year”
>28

## Slide 11: Programming and Production
24
25
26
27
28
23
Current Fiscal Year
Draft Transportation
Improvement Program (TIP)
“New 5th Year”
>28
Study
Design
Right-of-Way, Utilities
Environmental
Construction
Example of Major Projects Production

## Slide 12: Programming and Production
24
25
26
27
28
23
Current Fiscal Year
Draft Transportation
Improvement Program (TIP)
“New 5th Year”
>28
Design
Construction
Transportation Alternatives
Resurfacing, Restoration, Rehabilitation

## Slide 13: TIP Project Sections
Approved
TPA Priority List
TPA PRIORITY PROJECTS
  Major Projects/
  State Road Modifications
  Local Initiatives Program
  Transportation Alternatives Program
FDOT PRIORITIES AND OTHER PROJECTS
  Strategic Intermodal System (SIS) Capacity
  Other FDOT & Local Projects
  Airports, Railroads and Seaport
OPERATIONS AND MAINTENANCE
  Major Maintenance
  O&M Roadways
  O&M Transit

## Slide 14: Guide to Summary Tables
Year &
Priority
Common years
in adopted TIP
New 5th Year
added to TIP
Funding still
needed

## Slide 15: Strategic Intermodal System (SIS)
SIS Summary of Projects
Programmed: $1,488,020,385
Cost | Projects
$1,234M | Turnpike Widening Projects + 3 Interchanges
$439M | 15 I-95 Interchanges (New or Modified)

## Slide 16: I-95 Projects
 |  |  | <24 | 24 | 25 | 26 | 27 | 28 | >28
 | Indiantown Rd to Martin County | Widen to 8L |  | Study |  |  |  |  | 
 | Indiantown Rd |  | CST |  |  |  |  |  | 
 | Central Blvd | New TDI | PE |  |  |  |  |  | CST
 | Northlake Blvd |  | PE |  |  | CST |  |  | 
 | 45th St | DDI | PE |  |  | CST |  |  | 
 | Palm Beach Lakes Blvd |  | PE |  |  | CST |  |  | 
 | Southern Blvd |  |  |  | PE |  |  |  | CST
 | Forest Hill Blvd |  | PE |  |  | CST |  |  | 
 | 10th Ave N | DDI | PE |  |  |  |  |  | CST
 | 6th Ave S |  | PE |  | CST |  |  |  | 
 | Lantana Rd | DDI | PE |  |  |  |  |  | CST
 | Hypoluxo Rd | DDI | PE |  |  |  | CST |  | 
 | Gateway Blvd |  | PE |  |  |  | CST |  | 
 | Boynton Beach Blvd |  | PE |  | CST |  |  |  | 
 | Woolbright Rd |  | PE |  |  |  | CST |  | 
 | Linton Blvd |  | PE |  |  |  |  | CST | 
North
South
PE
Preliminary Engineering
CST
Construction
DDI
Diverging Diamond Interchange
TDI
Tight Diamond Interchange

## Slide 17: Turnpike Projects
 |  |  | <24 | 24 | 25 | 26 | 27 | 28 | >28
 | Indiantown Rd to Martin County | Widen to 8L |  |  | PE |  |  |  | CST
 | PGA Blvd to Indiantown Rd | Widen to 8L |  |  |  |  | PE |  | CST
 | Beeline Hwy to PGA Blvd | Widen to 8L |  | PE |  |  |  | CST | 
 | Okeechobee Blvd to Beeline Hwy | Widen to 8L |  | PE |  | CST |  |  | 
 | Southern Blvd to Okeechobee Blvd | Widen to 8L |  |  | CST |  |  |  | 
 | WPB Service Plaza to Southern Blvd | Widen to 8L |  | PE |  | CST |  |  | 
 | Boynton Beach Blvd | Ramps & Aux lanes | PE | CST |  |  |  |  | 
 | Hypoluxo Rd | New interchange |  |  |  | Study |  |  | 
 | Glades Rd | Improvements |  |  |  |  | PE |  | CST
 | N of Atlantic Ave to Boynton Beach Blvd | Ramps & Aux lanes |  |  |  |  |  | PE | CST
 | N of Glades Rd to S of Atlantic Ave | Widen to 10L |  | PE |  |  | CST |  | 
 | Broward County to N of Glades Rd | Widen to 8L | PE |  | CST |  |  |  | 
North
South
PE
Preliminary Engineering
CST
Construction
new
new
new
new

## Slide 18
Delray Beach/Boca Raton Brant Drive Bridge 2023

## Slide 19
Royal Palm Beach – FPL pathway lighting 2021

## Slide 20: Other New Projects
Resurfacing (FY 27)
  US-27 from MP 12.7 to MP 16
  Federal Hwy/SR-5 from US-1 to 10th Ave S
  SR-7 from S of SR-804/Boynton Beach Blvd to Lake Worth Rd
  Royal Palm Way from 4 Arts Plaza to S County Rd
  SR-717/E Canal St from SR-80 to SE Ave E
  Lake Worth Rd from Everett Ct to A St
  Forest Hill Blvd from east of Lake Clarke Drive to US-1
Resurfacing (FY 28)
  Beeline Hwy/SR-710 from west of Park Commerce Blvd to east of Aviation Blvd
Flavor Pict Rd from Lyons Rd to Hagen Ranch
Roadway Extension (FY 28)
  SR-706/Indiantown Rd Bridges (#930453 & 930454)
  SR-A1A/Ocean Blvd Bridge over Boca Inlet (#930060)
Bridge Rehab (FY 28)

## Slide 21: View Draft TIP
PalmBeachTPA.org/TIP
Executive Summary
Full Document
Link to Map
Appendices
  Glossary
  Public Participation
  Performance Measures
  Fiscal Analysis

## Slide 22: Provide Feedback
Improve clarity
Corrections
Submit local projects for reference
Final adoption in June

## Slide 23: Motion to Recommend Adoption FY 24-28 TIP